# Submission Readiness Checklist

## Purpose

This checklist separates the current manuscript status into two levels:

- MSc supervisor / progress-report readiness.

- Journal submission readiness.

The project is currently strong as an MSc research manuscript draft, but it is not yet ready for direct journal submission.

## Current Status Summary

The project now includes:

- Reproducible experiment scripts.

- Three trained model pipelines: ResNet18, EfficientNet-B0, and ViT-B/16.

- D1 internal evaluation.

- D2 overlap audit and rejection.

- D3B shifted-domain evaluation.

- Calibration and temperature scaling analysis.

- Generated tables.

- Generated figures.

- Manuscript draft.

- Figure and table captions.

- Citation placeholders.

- Reference tracking files.

- Citation integrity audit.

- AI use and citation integrity protocol.

Current status:

- MSc supervisor update: Ready.

- MSc thesis results chapter draft: Strong first draft.

- Journal submission: Not ready yet.

- Q1 journal submission: Not ready yet.

## MSc Supervisor-Ready Checklist

| Item | Status | Notes |
| --- | --- | --- |
| Clear research question | Complete | Focuses on reliability beyond internal accuracy |
| Reproducible environment | Complete | Environment and setup documentation exist |
| Dataset usage decisions | Complete | D1 used, D2 rejected, D3B used cautiously |
| Leakage / overlap auditing | Complete | D2 overlap and D1-D3B audit documented |
| Internal model training | Complete | E001, E002, E003 complete |
| Internal performance results | Complete | Table 2 and Figure 2 |
| Calibration results | Complete | Table 3 and Figure 3 |
| D3B shifted-domain results | Complete | Table 4 and Figures 4–5 |
| D3B temperature-scaled results | Complete | Table 5 and Figure 6 |
| Pipeline figure | Complete | Figure 1 |
| Manuscript draft | Complete | Draft includes Introduction, Methods, Results, Discussion, Conclusion |
| Citation placeholders | In progress | Placeholders inserted, but final citation style not applied |
| Literature integration | In progress | Reference backbone exists |
| Supervisor explanation quality | Strong | Suitable for showing progress and methodological maturity |

Judgment:

The project is ready to show to a supervisor as a serious MSc-level research update.

## Journal Submission-Ready Checklist

| Item | Status | Required action |
| --- | --- | --- |
| Final literature review | Not complete | Read and verify every cited paper fully |
| Final reference formatting | Not complete | Convert REF placeholders into target journal style |
| Target journal selected | Not complete | Choose journal before final formatting |
| Journal author guidelines checked | Not complete | Check word limits, figure limits, structure, AI policy |
| AI disclosure decision | Not complete | Follow target journal policy |
| Data availability statement | Not complete | Define what can be shared and what is restricted |
| Code availability statement | Not complete | Link GitHub repository once cleaned |
| Ethics / dataset use statement | Not complete | Clarify public dataset use and TCIA/D3B terms |
| Figure visual inspection | Not complete | Open every figure and verify readability |
| Table formatting | Not complete | Convert markdown tables to journal format |
| Abstract polish | Not complete | Needs journal-style abstract |
| Methods detail check | In progress | Needs final reproducibility pass |
| Statistical reporting check | Not complete | Ensure all metrics and sample counts are consistent |
| Limitations polish | In progress | Already conservative, but needs final journal style |
| External validation language check | In progress | Must avoid overclaiming D3B |
| Clinical claim check | In progress | Must avoid deployment or diagnostic-readiness claims |
| Supplementary material plan | Not complete | Decide what goes into supplement |
| Supervisor review | Not complete | Supervisor should review before journal targeting |
| Independent code/result check | Not complete | Ideally rerun key scripts or verify artifacts |

Judgment:

The manuscript is not journal-submission-ready yet. It needs literature verification, journal formatting, final reference conversion, and a stricter reporting pass.

## Critical Do-Not-Claim List

The manuscript must not claim:

- That D3B is full four-class external validation.

- That the models are clinically reliable.

- That the models are ready for deployment.

- That EfficientNet-B0 is universally superior.

- That ViT-B/16 is generally worse than CNNs.

- That temperature scaling solves dataset shift.

- That calibration is equivalent to full uncertainty estimation.

- That D2 was useless; the correct claim is that D2 was unsuitable as clean external validation because of overlap.

- That the study proves all brain MRI classifiers are unreliable.

- That the study is a clinical validation study.

## Defensible Core Claims

The manuscript can defensibly claim:

- High internal performance was achieved on D1.

- D2 was rejected as clean external validation due to substantial overlap with D1.

- D3B showed unstable glioma-focused shifted-domain behaviour.

- Temperature scaling improved internal calibration.

- Temperature scaling softened D3B confidence but did not change class predictions.

- Internal accuracy alone is insufficient evidence of reliability.

- Leakage-aware auditing, calibration, and shifted-domain testing provide a more conservative evaluation framework.

- The current study is a reproducible MSc-level reliability evaluation of brain MRI tumour classification models.

## Immediate Next Steps

- Convert citation placeholders into a final reference format after selecting a target style.

- Add a final reference list to the manuscript.

- Create data availability, code availability, and AI-use disclosure statements.

- Export the manuscript to DOCX or PDF for supervisor review.

- Ask the supervisor for methodological feedback before aiming at a journal.